## Sheet1
User Stories | Assignee | Task Description | Initial Estimate | Amount Remaining After
|  |  |  | Week 1 | Week 2
User - Add transportation to my trip | Jamia | Create add transportation GUi | 2 | 0 | 0
|  | Create transportation DAL | 5 | 1 | 0
|  | Create Transportation information GUI | 3 | 1 | 0
User - Remove Transportation from my trip | Jamia | Create remove event | 2 | 1 | 0
|  | Add Transportation DAL tests | 8 | 7 | 0
User - Add lodging to a trip | Austin | Create add Lodging GUI | 3 | 0 | 0
|  | Create Lodging information GUI | 3 | 0 | 0
|  | Create Lodging DAL | 8 | 1 | 0
User - Remove lodging from a trip | Austin | Create remove event | 2 | 1 | 0
|  | Add Lodging Tests | 8 | 7 | 0
Update Web Application | Brian | Create login with validation | 4 | 1 | 0
|  | Create trip page with validation | 6 | 2 | 0
|  | Create waypoints page with validation | 12 | 9 | 0
Not completed
Add/Remove Lodging
Add/Remove transportation