## Sheet1
User Stories | Assignee | Task Description | Initial Estimate | Amount Remaining After
|  |  |  | Week 1 | Week 2
User - View Transportation details with Google maps - Desktop | Jamia | Research Google map API/URL calls | 8 | 0 | 0
|  | Implement view transportation route info via google maps | 12 | 10 | 0
User - View Transportation details with Google maps - Web | Brian | Research Google map APIs for displaying route information | 8 | 0 | 0
|  | Implement view transportation route info via google maps | 12 | 10 | 0
Implement Estimated Travel Time for Create Transportation - Web | Austin | Research Google map APIs for calculating route distance | 8 | 0 | 0
|  | Implement estimated travel time based on type, origin, destination | 12 | 12 | 0
Not completed