## Sheet1
User Stories | Assignee | Task Description | Initial Estimate | Amount Remaining After
|  |  |  | Week 1 | Week 2
User - Create a Trip (name and start/end time) | Jamia | Create add task GUI | 4 | 4 | 0
Create Trip DAL
User - Add Waypoints (place + time) to my trip | Austin | Create add Waypoint GUI | 5 | 2 | 1
Create Waypoint GUI
User - Remove Waypoints from my trip | Austin | Create Remove Waypoint button | 5 | 3 | 1
User - View an overview of my trip | Jamia | Modify Trip overview page | 5 | 3 | 2
User - I want to log into the system | Brian | Create login page | 5 | 3 | 0
Create Login DAL