## Sheet1
User Stories | Assignee | Task Description | Initial Estimate | Amount Remaining After
|  |  |  | Week 1 | Week 2
User - Add transportation to my trip | Jamia | Create add transportation GUi | 2 | 0 | 0
|  | Create transportation DAL | 3 | 0 | 0
|  | Create Transportation information GUI | 2 | 2 | 0
User - Remove Transportation from my trip | Jamia | Create remove event | 1 | 1 | 0
|  | Add Transportation DAL tests | 4 | 2 | 0
User - Add lodging to a trip | Austin | Create add Lodging GUI | 2 | 0 | 0
|  | Create Lodging information GUI | 4 | 1 | 0
|  | Create Lodging DAL | 2 | 0 | 0
User - Remove lodging from a trip | Austin | Create remove event | 1 | 1 | 0
|  | Add Lodging Tests | 3 | 2 | 0
Update Web Application | Brian | Create login page | 4 | 1 | 0
|  | Modifiy add Transportation page | 2 | 2 | 0
|  | Modifiy add Trip page | 2 | 0 | 0
|  | Modifiy add lodging page | 2 | 1 | 0
|  | Modify add Waypoint page | 2 | 0 | 0