## Sheet1
User Stories | Assignee | Task Description | Initial Estimate | Amount Remaining After
|  |  |  | Week 1 | Week 2 | Week 3
User - Add transportation to my trip - web | Austin | Learn ASP | 5 | 5 | 1 | 0
|  | Implement add transportation functionality (with conflicts) | 12 | 11 | 9 | 0
User - Remove Transportation from my trip - web | Austin | Implement delete transportation functionality | 2 | 2 | 2 | 0
User - Add lodging to a trip - web | Brian | Implement add lodging with conflicts functionality | 6 | 6 | 0 | 0
User - Remove lodging from a trip - web | Brian | Implement remove lodging functionality | 3 | 3 | 0 | 0
Implement Google Maps View Waypoint - web | Brian | Implement google maps when viewing waypoint - web | 8 | 8 | 2 | 0
Implement Google Maps View Lodging - web | Brian | Implement google maps when viewing lodging - web | 8 | 8 | 5 | 0
Implement Google Maps View Waypoint - Desktop | Jamia | Implement google maps when viewing waypoint - desktop | 12 | 6 | 3 | 0
Implement Google Maps View Lodging - Desktop | Jamia | Implement google maps when viewing lodging - desktop | 12 | 12 | 8 | 0
Implement Unit Tests | Jamia | Desktop Model Integration Tests | 5 | 5 | 5 | 0
| Austin | Web - Transportation Controller Tests | 10 | 10 | 9 | 0
| Brian | Web - Controller Tests | 5 | 5 | 5 | 0
Not completed